## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-SWEN-261-02-6F JulianAndMs
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Helper, I want to add needs to my funding basket so I can keep track of what I want to contribute to. | Given A need is not added to a funding basket when I add to Funding Basket then The system returns 201 Created; Given a need is already in the funding basket when the user tries to add it to their funding basket then a status of FORBIDDEN (403) is returned the and the need is not added again. | Pass | AD; 3/18/2024
As a U-fund Manager, I want to remove needs from the cupboard so that helpers don’t see outdated needs. | GIVEN I submit a request to delete a need from the cupboard WHEN the need exists, THEN the need should be removed from the cupboard and return a status code of 200 (OK); GIVEN I submit a request to delete a need from the cupboard WHEN the need does not exist, THEN no need should be should be modified and the system should return a status code of 404 (NOT FOUND) | Pass | AD; 3/18/2024
As a Helper I want to remove needs from my funding basket so that I no longer have to contribute to the needs when I go to check-out. | Given a need is in their funding basket when the user removes a need from the funding basket then a status code of SUCCESS (200) is returned the need is removed from the funding basket; Given a need is not in the funding basket when the user tries to remove it from their funding basket then a status code of BAD REQUEST (400) is returned and nothing changes in the funding basket. | Pass | MZ; 3/18/2024
As a Manager, I want to access the U-fund cupboard securely with the username 'admin' so that no helpers or third-party actors can access it. | Given the username "admin" is input when the administrator is on the login screen then the administrator should log in with the correct privileges and the server should return a status code of 200. | Pass | SN; 3/18/2024
As a Helper, I want to access my funding basket securely with my own username so that no helpers or third-party actors can access it. | Given A valid username (i.e. not empty) is input when the helper is on the login screen then the user should log in and the server should return a status code of 200; Given an invalid username (i.e. the empty string) is input when the helper is on the login screen then a status code of BAD REQUEST (400) should be returned the user should be redirected back to the login page. | Pass | AD; 3/18/2024
As a User I want to have my own password so that my account remains secure. | Given I am creating a new account when I enter in my password then the system should save my password for when I log in later; Given I am logging in when I enter the correct password then the system should grant me access to my account; Given I am logging in when I enter a wrong password then the system should not grant me access to my account and let me know that the password is incorrect. | Pass | BS; 3/18/2024
As a user I want to search for needs within the cupboard so I can find needs that match what I am looking for. | Given that a need exists with the given filters, when a search is made, then a status code of 200 is returned and the needs that satisfy the filters are displayed; Given no needs exist with the given filters, when a search is made, then a status code of 200 is returned and an empty list is displayed. | Pass | BS; 3/18/2024
As a Developer I want to be able to contribute to a need so that its current quantity can be modified. | Given a need exists when I try to contribute a negative amount then I get a bad request error; Given a need does not exist when I try to contribute to it then I get a 404 error; Given a need exists when I try to contribute a positive amount then the need is updated and I get a status code of 200; Given that a need has been contributed to when the need is updated then currentQuantity amount should remain unchanged. | Pass | JA; 3/18/2024
As an admin I want to view the needs cupboard so that I can keep track of which needs are currently available. | GIVEN the administrator submits a request for needs WHEN needs exist in the cupboard THEN the system should return a list of needs and a status code of 200 (OK); GIVEN the administrator submits a request for needs WHEN no needs exist in the cupboard THEN the system should return an empty list of needs and a status code of 200 (OK) | Pass | AD; 3/18/2024
As a Manager, I want to edit the data of needs/volunteer work in the cupboard so that changing circumstances of a need can be reflected in the U-fund. | Given a needs exists when the administrator edits the data then the need is updated for the administrator and the helper. | Pass | BS; 3/18/2024
As a Helper, I want to view a list of needs from the needs cupboard so I can see which ways I can contribute. | Given that a Helper is logged in when they are on the browsing page then they can see a list of needs from the needs cupboard. | Pass | AD; 3/18/2024
As a U-fund Manager I want to add needs into the cupboard so that helpers know what we currently need. | GIVEN I submit a need object WHEN no need with the given name exists THEN the system should create the need, add it to the cupboard, save to the persistent storage, and return the need object and a status code of 201 (CREATED); GIVEN I submit a need object WHEN a need with the given name already exists THEN the system should return a status code of 409 (CONFLICT) | Pass | JA; 3/18/2024
As a Helper I want to check-out my selected needs so that I can confirm which needs I am contributing to. | Given the user has at least one need in their funding basket and they are all valid when they checkout the funding basket then the system should contribute to all the needs appropriately and return status code 200; Given the user has no needs in their funding basket when they checkout the funding basket then the system should notify the user that they have no needs selected and return status code 400. | Pass | MZ; 3/18/2024
As a user I want to change my username so that I feel more comfortable with how my account is set up. | Given I am logged in as a helper when I open my settings page then I should see an option to change my username. Given I am logged in as an admin when I open my settings page then I should NOT see an option to change my username. Given I am logged in as a helper when I change my username to an available username then the change should succeed. Given I am logged in as a helper when I change my username to a taken username then the change should fail and I should receive a warning.
As a user I want to be able to access a page with features related to my account. | Given I'm logged in when I click on the user settings tab then I have access to personalized user settings.
As an admin I want to have preset types for needs so that they can be handled differently. | Given I am logged in as an admin when I create a need then I should see a drop-down for the type that contains several preset types. Given I am logged in as an admin when I set the drop-down to the "Other" option then I should be able to enter a custom type.
As a user I want to be able to change my password, so that I can access my account even if I forgot the password. | Given the user forgets their password when they click the 'Forgot Password' then they will have the option to change their password. Given the user inputs two different passwords when confirming their password when they click the 'Forgot Password' then they will receive an error message. |  |  |  | The Forgot Password button has not been implemented yet.
As a Helper I want to filter my search so that I can choose needs with specific attributes. | Given a user has search filters active when they search for needs then a list of filtered needs is returned with a status code of 200.
As an admin I want to be able to view statistics on the needs in the cupboard so that I can gain insight into how helpers contribute to them. | Given I am logged in as admin when I navigate to view the statistics then I am redirected to the statistics page. Given I am logged in as a helper when I try to access the statistics page then the website should route me elsewhere. |  |  |  | This story has not been implemented yet.